Phase 1: Business & Problem Understanding

Goal: Define the scientific "why" and set the project scope.

- Tasks: Formalize the Research Questions (e.g., "Can initial brain volume predict conversion to dementia within 2 years?"). Define the Null ($H_0$) and Alternative ($H_1$) hypotheses.

- Assignment: Student 1 (Project Lead). This person sets the "Story" of the paper and ensures the introduction aligns with clinical research goals.

Phase 2: Data Understanding & Characterization

Goal: Profile the dataset to meet the first learning outcome.

- Tasks: Perform Exploratory Data Analysis (EDA). Create visualizations for class distributions (Demented, Nondemented, Converted). Analyze the distribution of the MMSE and nWBV variables.

- Assignment: Student 2 (Data Analyst). Responsible for the "Data Characterization" section of the paper, including summary statistics and normality testing.

Phase 3: Data Preparation (Wrangling)

Goal: Transform the raw CSV into a "Model-Ready" format.

- Tasks: Handle the "Longitudinal" aspect. You must decide whether to use only "Visit 1" data or calculate the "Delta" (change) between visits. Perform data imputation for missing SES values and standardize numerical features using Z-score scaling.

- Assignment: Student 3 (Machine Learning Engineer). This is the most code-heavy task. They must ensure the data is "flattened" so that the model doesn't "cheat" by seeing the same patient twice in training and testing.

Phase 4: Modeling

Goal: Build and tune the predictive engines.

- Tasks: Implement at least three supervised algorithms (e.g., Logistic Regression, Random Forest, and Support Vector Machines). Perform a Train/Test split (e.g., 80/20) ensuring no subject is in both sets.

- Assignment: Student 3 (Machine Learning Engineer). They develop the code that automates the inference.

Phase 5: Evaluation & Critical Analysis

Goal: Measure success using the metrics defined in the module.

- Tasks: Generate 3x3 Confusion Matrices for the multi-class problem. Calculate Sensitivity (Recall), Precision, and F1-Score for each group. Specifically, analyze Type II errors (missing a diagnosis) and their clinical implications.

- Assignment: Student 4 (Evaluation Specialist). This person writes the "Results" and "Discussion" sections, comparing the performance of the three models.

Phase 6: LSEP & Sustainability Analysis

Goal: Address the Legal, Social, Ethical, and Professional requirements.

- Tasks: Analyze the project through the lens of GDPR (Data Minimization). Discuss the Social impact of predicting "Conversion" and the Professional responsibility of model transparency (Explainable AI). Discuss the sustainability of the code (Maintainability and Reproducibility).

- Assignment: Student 1 & Student 4. This requires deep critical thinking and is a significant portion of the marks.

Phase 7: Final Deliverables (The Video & Paper)

Goal: Package the work for submission.

- Tasks: Record the video demonstration. Each member must present their specific contribution to show individual understanding. Finalize the research paper, ensuring all code is commented and reusable.

- Assignment: All Members. Student 1 typically handles the final video editing and submission formatting.